## Stage 0
Carbon Decision Matrix
Stage 0 | Strategic Definition
Brief
Review relevant current and emerging carbon and energy policy and legistlation. Planning requirements for the Project. Initial engagment with stakeholders. Set the Carbon context for the project, including Net Zero Carbon Goals. Review relevant preticent projects and any Post Occupancy Evaluation (POE) data available. Identify Carbon and Energy Outcomes for the project. Consider Building longevity in terms of Whole Life Carbon, climate change, adaptability and operation. Carbon and Energy Strategy Integrated into the Business Case and Strategic Brief. Assess the Carbon and Energy opportunities and contraints of potential sites and building assets.
10 Steps
Site planning and building form. | Design Team to populate with decisions taken at this stage
Optimising façades.
Optimising construction strategy and materials.
Design for performance.
Specifying efficient landlords systems.
Recommending efficient tenant systems.
Specifying intelligent controls/ capturing data.
Managing occupant expectations.
Specifying on-site renewables.
Monitoring and verification
Delivery
Review of potential site(s) including re-use of existing buildings, components or materials. Schedule required Specialists and surveys.
Stage Outputs
Produce Carbon Vision Document aligned with Business Case and Strategic Brief.

## Stage 1
Carbon Decision Matrix
Stage 1 | Preparation and Briefing
Brief
Review relevant current and emerging carbon and energy policy and legistlation. Planning requirements for the Project. Initial engagment with stakeholders. Set the Carbon context for the project, including Net Zero Carbon Goals. Review relevant preticent projects and any Post Occupancy Evaluation (POE) data available. Identify Carbon and Energy Outcomes for the project. Consider Building longevity in terms of Whole Life Carbon, climate change, adaptability and operation. Carbon and Energy Strategy Integrated into the Business Case and Strategic Brief. Assess the Carbon and Energy opportunities and contraints of potential sites and building assets.
10 Steps
Site planning and building form. | Design Team to populate with decisions taken at this stage
Optimising façades. | Design Team to populate with decisions taken at this stage
Optimising construction strategy and materials.
Design for performance.
Specifying efficient landlords systems.
Recommending efficient tenant systems.
Specifying intelligent controls/ capturing data.
Managing occupant expectations.
Specifying on-site renewables.
Monitoring and verification
Delivery
Review of potential site(s) including re-use of existing buildings, components or materials. Schedule required Specialists and surveys.
Stage Outputs
Site Specific Carbon Vision and Implementation Plan incorportated into the Project Brief. Carbon Outcomes defined, understood and with buy in from all parties and stakeholders.

## Stage 2
Carbon Decision Matrix
Stage 2 | Concept Design
Brief
Review relevant current and emerging carbon and energy policy and legistlation. Planning requirements for the Project. Initial engagment with stakeholders. Set the Carbon context for the project, including Net Zero Carbon Goals. Review relevant preticent projects and any Post Occupancy Evaluation (POE) data available. Identify Carbon and Energy Outcomes for the project. Consider Building longevity in terms of Whole Life Carbon, climate change, adaptability and operation. Carbon and Energy Strategy Integrated into the Business Case and Strategic Brief. Assess the Carbon and Energy opportunities and contraints of potential sites and building assets.
10 Steps
Site planning and building form. | Design Team to populate with decisions taken at this stage
Optimising façades. | Design Team to populate with decisions taken at this stage
Optimising construction strategy and materials. | Design Team to populate with decisions taken at this stage
Design for performance. | Design Team to populate with decisions taken at this stage
Specifying efficient landlords systems. | Design Team to populate with decisions taken at this stage
Recommending efficient tenant systems. | Design Team to populate with decisions taken at this stage
Specifying intelligent controls/ capturing data. | Design Team to populate with decisions taken at this stage
Managing occupant expectations.
Specifying on-site renewables. | Design Team to populate with decisions taken at this stage
Monitoring and verification
Delivery
Review of potential site(s) including re-use of existing buildings, components or materials. Schedule required Specialists and surveys.
Stage Outputs
Update the Carbon Implementation Plan. The Concept Design integrates the Carbon Vision and Implementation Plan with the Final Project Brief and verified against the Carbon and Energy Outcomes.

## Stage 3
Carbon Decision Matrix
Stage 3 | Spatial Coordination
Brief
Review relevant current and emerging carbon and energy policy and legistlation. Planning requirements for the Project. Initial engagment with stakeholders. Set the Carbon context for the project, including Net Zero Carbon Goals. Review relevant preticent projects and any Post Occupancy Evaluation (POE) data available. Identify Carbon and Energy Outcomes for the project. Consider Building longevity in terms of Whole Life Carbon, climate change, adaptability and operation. Carbon and Energy Strategy Integrated into the Business Case and Strategic Brief. Assess the Carbon and Energy opportunities and contraints of potential sites and building assets.
10 Steps
Site planning and building form.
Optimising façades. | Design Team to populate with decisions taken at this stage
Optimising construction strategy and materials. | Design Team to populate with decisions taken at this stage
Design for performance. | Design Team to populate with decisions taken at this stage
Specifying efficient landlords systems. | Design Team to populate with decisions taken at this stage
Recommending efficient tenant systems. | Design Team to populate with decisions taken at this stage
Specifying intelligent controls/ capturing data. | Design Team to populate with decisions taken at this stage
Managing occupant expectations.
Specifying on-site renewables. | Design Team to populate with decisions taken at this stage
Monitoring and verification
Delivery
Review of potential site(s) including re-use of existing buildings, components or materials. Schedule required Specialists and surveys.
Stage Outputs
Refine the Carbon Implementation Plan. The Services, structural and architectural design are coordinated with the CIP which is included in statutory submissions. Develop a seasonal controls strategy.

## Stage 4
Carbon Decision Matrix
Stage 4 | Technical Design
Brief
Review relevant current and emerging carbon and energy policy and legistlation. Planning requirements for the Project. Initial engagment with stakeholders. Set the Carbon context for the project, including Net Zero Carbon Goals. Review relevant preticent projects and any Post Occupancy Evaluation (POE) data available. Identify Carbon and Energy Outcomes for the project. Consider Building longevity in terms of Whole Life Carbon, climate change, adaptability and operation. Carbon and Energy Strategy Integrated into the Business Case and Strategic Brief. Assess the Carbon and Energy opportunities and contraints of potential sites and building assets.
10 Steps
Site planning and building form.
Optimising façades. | Design Team to populate with decisions taken at this stage
Optimising construction strategy and materials. | Design Team to populate with decisions taken at this stage
Design for performance. | Design Team to populate with decisions taken at this stage
Specifying efficient landlords systems. | Design Team to populate with decisions taken at this stage
Recommending efficient tenant systems. | Design Team to populate with decisions taken at this stage
Specifying intelligent controls/ capturing data. | Design Team to populate with decisions taken at this stage
Managing occupant expectations.
Specifying on-site renewables. | Design Team to populate with decisions taken at this stage
Monitoring and verification
Delivery
Review of potential site(s) including re-use of existing buildings, components or materials. Schedule required Specialists and surveys.
Stage Outputs
Carbon and Energy requirements verified agaist Technical design.

## Stage 5
Carbon Decision Matrix
Stage 5 | Manufacturing and Construction
Brief
Review relevant current and emerging carbon and energy policy and legistlation. Planning requirements for the Project. Initial engagment with stakeholders. Set the Carbon context for the project, including Net Zero Carbon Goals. Review relevant preticent projects and any Post Occupancy Evaluation (POE) data available. Identify Carbon and Energy Outcomes for the project. Consider Building longevity in terms of Whole Life Carbon, climate change, adaptability and operation. Carbon and Energy Strategy Integrated into the Business Case and Strategic Brief. Assess the Carbon and Energy opportunities and contraints of potential sites and building assets.
10 Steps
Site planning and building form.
Optimising façades.
Optimising construction strategy and materials. | Design Team to populate with decisions taken at this stage
Design for performance.
Specifying efficient landlords systems.
Recommending efficient tenant systems.
Specifying intelligent controls/ capturing data. | Design Team to populate with decisions taken at this stage
Managing occupant expectations.
Specifying on-site renewables.
Monitoring and verification
Delivery
Review of potential site(s) including re-use of existing buildings, components or materials. Schedule required Specialists and surveys.
Stage Outputs
Building User Guides. Tenant Fit Out Guides.

## Stage 6
Carbon Decision Matrix
Stage 6 | Handover
Brief
Review relevant current and emerging carbon and energy policy and legistlation. Planning requirements for the Project. Initial engagment with stakeholders. Set the Carbon context for the project, including Net Zero Carbon Goals. Review relevant preticent projects and any Post Occupancy Evaluation (POE) data available. Identify Carbon and Energy Outcomes for the project. Consider Building longevity in terms of Whole Life Carbon, climate change, adaptability and operation. Carbon and Energy Strategy Integrated into the Business Case and Strategic Brief. Assess the Carbon and Energy opportunities and contraints of potential sites and building assets.
10 Steps
Site planning and building form.
Optimising façades.
Optimising construction strategy and materials.
Design for performance.
Specifying efficient landlords systems.
Recommending efficient tenant systems.
Specifying intelligent controls/ capturing data. | Design Team to populate with decisions taken at this stage
Managing occupant expectations. | Design Team to populate with decisions taken at this stage
Specifying on-site renewables.
Monitoring and verification
Delivery
Review of potential site(s) including re-use of existing buildings, components or materials. Schedule required Specialists and surveys.
Building user guides issued.
FM Team trained on Building Systems. As installed Carbon and Energy Targets verified.

## Stage 7
Carbon Decision Matrix
Stage 7 | Use
Brief
Review relevant current and emerging carbon and energy policy and legistlation. Planning requirements for the Project. Initial engagment with stakeholders. Set the Carbon context for the project, including Net Zero Carbon Goals. Review relevant preticent projects and any Post Occupancy Evaluation (POE) data available. Identify Carbon and Energy Outcomes for the project. Consider Building longevity in terms of Whole Life Carbon, climate change, adaptability and operation. Carbon and Energy Strategy Integrated into the Business Case and Strategic Brief. Assess the Carbon and Energy opportunities and contraints of potential sites and building assets.
10 Steps
Site planning and building form.
Optimising façades.
Optimising construction strategy and materials.
Design for performance.
Specifying efficient landlords systems.
Recommending efficient tenant systems.
Specifying intelligent controls/ capturing data. | Design Team to populate with decisions taken at this stage
Managing occupant expectations.
Specifying on-site renewables.
Monitoring and verification | Design Team to populate with decisions taken at this stage
Delivery
Review of potential site(s) including re-use of existing buildings, components or materials. Schedule required Specialists and surveys.
Stage Outputs
Knowledge shared across other projects. Assist with performance in use improvements.